## Documentation
Canvas Scribe
Author | Michael Feinbaum
Date | 2021-07-22
Purpose | To estimate the production schedule for a new game to be released by Canvas Scribe

## Production Schedule
Canvas Scribe
Production Schedule for Escape from Dunkirk
Summary
Start Date | 2025-08-19 17:56 |  | Work on Escape from Dunkirk must begin no later than 8/23/2021 in order to meet the 10/12/2022 release date for holiday sales.
Release Date | 2026-10-12
Total Working Days | 290
Total Calendar Days | 418.2525
Phase | Start Date | End Date | Workdays to Complete | Phase Starts |  | Holidays
Idea Development | 2025-08-19 17:56 | 2025-09-03 | 10 | 0 | Start Date | 2025-01-01
Story Writing | 2025-09-04 | 2025-09-25 | 15 | 1 | workday after the Idea Development end date | 2025-01-20
Character/Visual Design | 2025-09-26 | 2025-12-02 | 45 | 1 | workday after the Story Writing end date | 2025-05-26
Initial Story Boarding | 2025-09-26 | 2025-12-02 | 45 | 1 | workday after the Story Writing end date | 2025-07-04
Story Boarding Final Edits | 2025-12-03 | 2026-01-28 | 35 | 1 | workday after the Initial Story Boarding end date | 2025-09-01
Digital Animation | 2026-01-29 | 2026-05-14 | 75 | 1 | workday after the Story Boarding Final Edits end date | 2025-11-26
Rough Sound | 2026-01-29 | 2026-02-19 | 15 | 1 | workday after the Story Boarding Final Edits end date | 2025-11-27
Backgrounds | 2025-12-04 | 2026-03-26 | 75 | 2 | workdays after the Character/Visual Design end date | 2025-12-24
Character Animation | 2025-12-04 | 2026-03-26 | 75 | 2 | workdays after the Character/Visual Design end date | 2025-12-25
Initial Animation Effects | 2026-02-23 | 2026-05-11 | 55 | 2 | workdays after the Rough Sound end date | 2025-12-31
Cleanup Animation Effects | 2026-05-12 | 2026-06-03 | 15 | 1 | workday after the Initial Animation Effects end date | 2026-01-01
Digital Coloring | 2026-01-12 | 2026-05-05 | 80 | 25 | workdays after the Initial Storyboarding end date | 2026-01-19
First Edit | 2026-06-04 | 2026-06-18 | 10 | 1 | workday after the Cleanup Animation Effects end date | 2026-05-25
Testing | 2026-06-19 | 2026-07-17 | 20 | 1 | workday after the First Edit end date | 2026-07-04
Revisions | 2026-07-20 | 2026-08-17 | 20 | 1 | workday after the Testing end date | 2026-09-07
Second Testing | 2026-08-18 | 2026-09-01 | 10 | 1 | workday after the Revisions end date | 2026-11-25
Final Approval | 2026-09-02 | 2026-09-10 | 5 | 1 | workday after the Second Testing end date | 2026-11-26
Production | 2026-09-11 | 2026-10-09 | 20 | 1 | workday after the Final Approval end date | 2026-12-24
Release | 2026-10-12 | 2026-10-12 | 0 | 1 | workday after the Production end date | 2026-12-25
2026-12-31
Formulas:
Start Date = WORKDAY([End Date, row above],[Phase Starts],H10:H29)
Start Date = WORKDAY(C11,[Phase Starts],H10:H29)
End Date = WORKDAY([Start Date],[Workdays to Complete],H10:H29)