|  | Pinero Construction |
| --- | --- |

To:	Anna Lopez

From:	David Banks

Date:	5/1/2024

Re:	Construction Schedule

Anna,

Here is the current construction schedule for your new house on 414 Mountain View Drive in Coeur d’Alene, Idaho. Please look over the schedule and let us know if you have any concerns.

| Construction Phase | Start Date | End Date | Duration |
| --- | --- | --- | --- |
| Pre-Construction | 9/3/2024 | 10/3/2024 | 30 days |
| Site Setup | 10/4/2024 | 11/14/2024 | 41 days |
| Exterior Work | 10/10/2024 | 1/9/2025 | 91 days |
| Interior Work | 12/27/2024 | 4/28/2025 | 122 days |
| Finishing | 4/29/2025 | 6/16/2025 | 48 days |
| TOTAL | 9/3/2024 | 6/16/2025 | 286 days |

The following chart provides a visual overview of the construction timeline.

Regards,

David Banks
Construction Manager
Pinero Construction