## Documentation
Pinero Construction
Author | David Banks
Date | 2024-03-01
Purpose | To create a construction schedule for a new home created by Pinero Construction

## Timeline Summary
Pinero Construction
Home Construction Timeline
Owner | Anna Lopez
Address | 414 Mountain View Drive
City | Coeur d'Alene
State | Idaho
Postal Code | 83814

## Timeline Details
Pinero Construction
Home Construction Schedule
Phase | Task | Start Date | End Date | Workdays | Calendar Days | Construction Phase | Start Date | End Date | Duration | Holiday Dates
Pre-Construction | Start date | 2024-09-03 | 2024-09-11 | 6 | 8 | Pre-Construction | 2024-09-03 | 2024-10-03 | 30 | 2024-11-28
Pre-Construction | Demo prep | 2024-09-12 | 2024-09-18 | 4 | 6 | Site Setup | 2024-10-04 | 2024-11-14 | 41 | 2024-11-29
Pre-Construction | Demolition | 2024-09-19 | 2024-10-03 | 10 | 14 | Exterior Work | 2024-10-10 | 2025-01-09 | 91 | 2024-12-24
Site Setup | Excavation | 2024-10-04 | 2024-10-09 | 3 | 5 | Interior Work | 2024-12-27 | 2025-04-28 | 122 | 2024-12-25
Site Setup | Concrete | 2024-10-10 | 2024-10-23 | 9 | 13 | Finishing | 2025-04-29 | 2025-06-16 | 48 | 2024-12-31
Site Setup | Pre backfill | 2024-10-24 | 2024-10-25 | 1 | 1 | TOTAL | 2024-09-03 | 2025-06-16 | 286 | 2025-01-01
Site Setup | Framing | 2024-10-04 | 2024-11-14 | 29 | 41 |  |  |  |  | 2025-05-26
Exterior Work | Roof | 2024-10-28 | 2024-11-18 | 15 | 21 |  |  |  |  | 2025-07-04
Exterior Work | Plumbing | 2024-10-10 | 2024-11-20 | 29 | 41 |  |  |  |  | 2025-09-01
Exterior Work | Windows | 2024-10-24 | 2024-11-15 | 16 | 22 |  |  |  |  | 2025-11-27
Exterior Work | HVAC | 2024-10-28 | 2024-11-18 | 15 | 21 |  |  |  |  | 2025-11-28
Exterior Work | Electrical | 2024-11-21 | 2024-12-06 | 9 | 15 |  |  |  |  | 2025-12-24
Exterior Work | A/V | 2024-11-21 | 2024-11-27 | 4 | 6 |  |  |  |  | 2025-12-25
Exterior Work | House wrap | 2024-12-10 | 2024-12-12 | 2 | 2 |  |  |  |  | 2025-12-31
Exterior Work | Insulation | 2024-10-28 | 2024-11-14 | 13 | 17
Exterior Work | Drywall | 2024-12-16 | 2025-01-09 | 14 | 24
Exterior Work | Exterior stone | 2024-12-16 | 2025-01-03 | 10 | 18
Exterior Work | Exterior case work | 2024-12-16 | 2024-12-26 | 6 | 10
Interior Work | Utility flooring | 2025-01-10 | 2025-02-03 | 16 | 24
Interior Work | Hardwoods | 2024-12-27 | 2025-02-19 | 36 | 54
Interior Work | Tile | 2025-02-26 | 2025-03-10 | 8 | 12
Interior Work | Cabinets and fixtures | 2024-12-27 | 2025-02-04 | 25 | 39
Interior Work | Interior plumbing | 2025-03-11 | 2025-03-18 | 5 | 7
Interior Work | Interior doors | 2025-03-11 | 2025-03-24 | 9 | 13
Interior Work | Millwork | 2025-03-11 | 2025-03-12 | 1 | 1
Interior Work | Interior painting | 2025-03-11 | 2025-04-15 | 25 | 35
Interior Work | Stone counters | 2025-04-22 | 2025-04-28 | 4 | 6
Interior Work | Decks | 2025-03-11 | 2025-03-28 | 13 | 17
Interior Work | Interior doors | 2025-03-11 | 2025-03-20 | 7 | 9
Interior Work | Appliances | 2025-04-16 | 2025-04-17 | 1 | 1
Interior Work | General plumbing | 2025-04-16 | 2025-04-22 | 4 | 6
Interior Work | Electrical | 2025-04-16 | 2025-04-24 | 6 | 8
Interior Work | Bathroom glass | 2025-04-16 | 2025-04-21 | 3 | 5
Interior Work | Garage door | 2025-04-24 | 2025-04-28 | 2 | 4
Finishing | FINAL inspections | 2025-04-29 | 2025-04-30 | 1 | 1
Finishing | Final trim | 2025-05-01 | 2025-05-29 | 19 | 28
Finishing | Cleaning | 2025-05-30 | 2025-06-12 | 9 | 13
Finishing | Completion | 2025-06-13 | 2025-06-16 | 1 | 3
Formulas:
End Date = WORKDAY([Start Date],[Workdays],holidays)
End Date = MAXIFS(D5:D42,A5:A42,[Construction Phase])
Start Date = MINIFS(C5:C42,A5:A42,[Construction Phase])
Start Date = WORKDAY([End Date, row above],1,holidays)
Note on E39: David Banks: Contact Linda Olzchak 555-8711 to verify appointment with building inspector.

## Gantt Chart
Pinero Construction
Gantt Chart of Construction Schedule